## Rollout checklist
Purchasing Software Rollout Checklist
Stage | Check | Suggested owner | Acceptance evidence | Assigned owner | Observed result | Evidence reference | Status
Scope | Name one supplier, item group, destination and pilot order | Buyer | Written pilot scope and an authorized sender |  |  |  | Not started
Account access | Confirm connection permissions and intended locations | Account administrator | The agreed accounts and locations are connected |  |  |  | Not started
Item mapping | Check supplier item, sellable variant, unit and buying pack | Catalog owner | A case-to-unit conversion reconciles for each pilot item |  |  |  | Not started
Opening stock | Compare starting stock in both systems at the same time | Receiving lead | Quantity differences are explained before the pilot |  |  |  | Not started
Order ownership | Choose the only system allowed to send the pilot PO | Buyer | One supplier order is sent, with its reference retained |  |  |  | Not started
Supplier changes | Review a price change and split delivery | Buyer | Approved price, quantity and delivery plan have supporting evidence |  |  |  | Not started
Partial receipt | Record what arrived and reconcile the quantity still due | Receiving lead | One accepted receipt and a correct open balance |  |  |  | Not started
Connected stock | Check the mapped item and location after the receipt | Account administrator | The intended stock change appears once at the intended destination |  |  |  | Not started
Accounting | Review the proposed bill against supplier documents and receipts | Finance owner | Vendor, quantities, prices and required accounting fields are approved |  |  |  | Not started
Exceptions | Agree who investigates a missing or failed update before retrying | Operations owner | A named owner can explain how to reconcile and safely resume |  |  |  | Not started
Cutover | Record open orders and the date new ordering moves to the new process | Operations owner | Every open order has one owner and one receiving path |  |  |  | Not started
Decision | Review evidence and unresolved exceptions with each owner | Business owner | A recorded expand, revise or stop decision |  |  |  | Not started